## Slide 1: Project Management
C Business Services, LLC

## Slide 2: Story Outline
Define adventure & Project
Initiate
Plan
Execute
Monitor/control
close

## Slide 3: Definitions
CHOOSE ADVENTURE
Every few chapters – make a decision
PROJECT
A temporary endeavor to create a unique product/
service/result
PROJECT MANAGEMENT
Application of knowledge, skills, tools, and techniques
to project activities to meet project requirements

## Slide 4: Which one is a project?
New Policy for Alaska Paid Sick Leave Act
Move Clinic to New Space
Hire New Medical Assistant

## Slide 5: Which Adventure Shall We Do?
New Policy for Alaska Paid Sick Leave Act
Move Clinic to New Space
Hire New Medical Assistant

## Slide 6: Policy Development
Let the adventure begin

## Slide 7: Getting Starting - Initiation
Project Charter – Authorization to Write Policy
Identify Stakeholders
Notes: Charter – Authorization, Business Case, Statement

## Slide 8: Project Charter
Does the Owner know that the policy is needed and supports it?
Does the Administrator (PM) have the authority to write the policy and implement?

## Slide 9
If you confirm a project charter, A
If you proceed without a project charter, B

## Slide 10: Stakeholders
Who is impacted by the policy?
Who must change workflows because of policy?
Is there anyone outside of the organization who should know about the implementation of policy?
Is there anyone outside of the organization who have requirements related to the policy?

## Slide 11
If you list out stakeholders, C
If you do not list stakeholders, D

## Slide 12: Planning
Scope
Schedule
Cost
Quality
Resources
Communication
Risk
Procurement
Stakeholders

## Slide 13: Scope – North Star
External Requirements – AK Law
Deliverables – Policy and Procedure for payroll accrual/usage of leave
Boundaries – Assumptions, Constraints, Exclusions
Work Breakdown – Major steps/deliverables
What Does Done Look Like?

## Slide 14: Schedule
Start with the end in mind – Alaska requires implementation by July 2025
Determine timeline for each major step/deliverables

## Slide 15: Cost & Quality
Creating a policy/procedure doesn’t typically incur a cost but achieving goals of policy might
The quality of creating a policy/procedure is based on if outcomes meet goals – how do you measure?

## Slide 16: Resources
Payroll system
Experts
Staff
Colleagues

## Slide 17: Communication
Staff meetings
Memos
Emails
Timing – how often

## Slide 18
If you communicate throughout project, E
If you communicate at the beginning and end of the project, F

## Slide 19: Risk and Procurement
What risk is there in creating a new policy/procedure?
Procurement needed?

## Slide 20: Stakeholders
Did you choose C or D?

## Slide 21: Stakeholders
Who is impacted by the policy?
Who must change workflows because of policy?
Is there anyone outside of the organization who should know about the implementation of policy?
Is there anyone outside of the organization who have requirements related to the policy?

## Slide 22: Execution
Direct and Manage Work
Manage Project Knowledge
Manage Quality
Acquire Resources
Develop and Manage Team
Manage Communications
Implement Risk Response
Conduct Procurements
Manage Stakeholder Engagement

## Slide 23: Direct and Manage Work
Track Progress of Policy Development
Track Changes in Workflows
Tools: SharePoint, Monday, Excel, Meetings

## Slide 24: Project Charter
Did you choose A or B?
Notes: Do you really have the authority?

## Slide 25: Resources - Team
Virtual or In-person
Team Charter – not usually needed for 1 policy
Assignments

## Slide 26: Communication
Did you choose E or F?
Notes: All the time or Now/Later? How does that play out?

## Slide 27: Communication
Tools: Email, Whiteboard, Newsletter, Meetings
Training on New Policy
Reporting on PSL Balances

## Slide 28: Risk and Procurement
Low Risk and No Procurement for Policy Development

## Slide 29: Stakeholders
Engagement
Feedback
Updates

## Slide 30: Monitor and Control
Change Management
Validate and Control Scope
Schedule
Costs
Quality
Resources
Communication and Risk
Procurements
Stakeholders

## Slide 31: Change Management
Explain Change to Stakeholders
Plan for Resistance and Manage
Communicate, Ask for Feedback
Champion of Change

## Slide 32: Scope
Validate – Back to “What does done look like?”
Control (Scope creep)

## Slide 33: Schedule
On Task – 1 Policy
On Time – By July 2025

## Slide 34: Costs
Any Purchases?

## Slide 35: Quality
Policy Clear, Concise, Easy to Follow?
Metrics

## Slide 36: Resources
Bottlenecks?

## Slide 37: Communication
Communication According to Plan
Need More? Less?
Is the Earlier Decision Affecting Policy Development and Implementation?

## Slide 38: Risk and Procurement
Have Any Risks Become Issues?
Purchases Made As Needed?

## Slide 39: Stakeholders
Engaged?
Interest and Influence Managed?
Anyone We Missed?

## Slide 40: Close Out Policy Development
Policy Completed
Policy Implemented
Staff Accruing PSL As Planned
Home
End

## Slide 41: Move Clinic
Let the adventure begin

## Slide 42: Getting Starting - Initiation
Project Charter
  Goals – Pick location? Or just move?
  Authorization – To choose location and move clinic
Identify Stakeholders
Notes: Charter – Authorization, Business Case, Statement

## Slide 43: Project Charter
Does the Owner support moving to a new location? Are they in charge of picking new location?
Does the Administrator (PM) have the authority to coordinate all pieces to move to new location?

## Slide 44
If you confirm a project charter, A
If you proceed without a project charter, B

## Slide 45: Stakeholders
Who is impacted by the move?
Who must change workflows because of move?
Is there anyone outside of the organization who should know about the move?
Is there anyone outside of the organization who have requirements related to the move?

## Slide 46
If you list out stakeholders, C
If you do not list stakeholders, D

## Slide 47: Planning
Scope
Schedule
Cost
Quality
Resources
Communication
Risk
Procurement
Stakeholders

## Slide 48: Scope – North Star
External Requirements – Laws? Community?
Deliverables – Choosing new location, furniture/equipment move/purchase, start up at new location
Boundaries – Assumptions, Constraints, Exclusions
Work Breakdown – Major steps/deliverables
What Does Done Look Like?
Notes: Is the clinic allowed to be closed for the move? Are we phasing a move?

## Slide 49: Schedule
Start with the end in mind – Want to be in new place by X month.
Determine timeline for each major step/deliverables
  Choose location
  Sign lease
  Order furniture/equipment
  Close and move clinic

## Slide 50: Cost & Quality
New lease estimated cost
New furniture/equipment estimated costs
Expected quality of new space
  Better patient care?
  More services?

## Slide 51: Resources
Experts
Staff
Colleagues
Notes: Real estate agent

## Slide 52: Communication
Staff meetings
Memos
Emails
Timing – how often

## Slide 53
If you communicate throughout project, E
If you communicate at the beginning and end of the project, F

## Slide 54: Risk and Procurement
What risk is there in moving to a new location?
What needs to be purchased before/after move?
What are purchasing requirements?

## Slide 55: Stakeholders
Did you choose C or D?

## Slide 56: Stakeholders
Who is impacted by the move?
Who must change workflows because of move?
Is there anyone outside of the organization who should know about the move?
Is there anyone outside of the organization who have requirements related to the move?

## Slide 57: Execution
Direct and Manage Work
Manage Project Knowledge
Manage Quality
Acquire Resources
Develop and Manage Team
Manage Communications
Implement Risk Response
Conduct Procurements
Manage Stakeholder Engagement

## Slide 58: Direct and Manage Work
Track Progress of Deliverables
  Location chosen
  Furniture/Equipment purchased
  Move scheduled (packing complete)
Track Changes in Plan
Tools: SharePoint, Monday, Excel, Meetings

## Slide 59: Project Knowledge
Layout of New Space
Items to be Purchased
Lessons Learned

## Slide 60: Project Charter
Did you choose A or B?
Notes: Do you really have the authority?

## Slide 61: Quality
Location
Equipment/Furniture
Metrics

## Slide 62: Resources - Team
Virtual or In-person
Team Charter
Assignments
Schedules
Training
Team Building

## Slide 63: Communication
Did you choose E or F?
Notes: All the time or Now/Later? How does that play out?

## Slide 64: Communication
Tools: Email, Whiteboard, Newsletter, Meetings
Training
Reporting on Move Status

## Slide 65: Risk and Procurement
Risk Mitigation – extra insurance for move
Risk Becomes Issue - when it happens
Purchasing – RFP, RFB, Quotes
Contracts

## Slide 66: Stakeholders
Engagement
Feedback
Updates

## Slide 67: Monitor and Control
Change Management
Validate and Control Scope
Schedule
Costs
Quality
Resources
Communication and Risk
Procurements
Stakeholders

## Slide 68: Quality
Data Analysis
Metrics
Audits
Testing Outcomes

## Slide 69: Change Management
Explain Change to Stakeholders
Plan for Resistance and Manage
Communicate, Ask for Feedback
Champion of Change

## Slide 70: Scope
Validate – Back to “What does done look like?”
Control (Scope creep)

## Slide 71: Schedule
On Task
On Time

## Slide 72: Costs
New Lease Within Range
Equipment/Furniture Costs Controlled (in budget)
Movers (who’s packing?)

## Slide 73: Quality
Metrics for Done
  Patients arriving at new location
  New location not cluttered with boxes from move
  Old location cleared out and clean

## Slide 74: Resources
Bottlenecks?

## Slide 75: Communication
Communication According to Plan
Need More? Less?
Is the Earlier Decision Affecting Moving?

## Slide 76: Risk and Procurement
Have Any Risks Become Issues?
Purchases Made As Needed?

## Slide 77: Stakeholders
Engaged?
Interest and Influence Managed?
Anyone We Missed?

## Slide 78: Close Out Move Clinic
Move Completed
Old Lease Completed
Lessons Learned
Home
End

## Slide 79: Hire Staff
Let the adventure begin

## Slide 80: Getting Starting - Initiation
Project Charter
  Goals – 1 Medical Assistant
  Authorization – To Choose and Hire
Identify Stakeholders
Notes: Charter – Authorization, Business Case, Statement

## Slide 81: Project Charter
Does the Owner support hiring new staff? Are they participating in hire?
Does the Administrator (PM) have the authority to coordinate all pieces to hire new staff?

## Slide 82
If you confirm a project charter, A
If you proceed without a project charter, B

## Slide 83: Stakeholders
Who is impacted by the hire?
Who must change workflows because of hire?
Is there anyone outside of the organization who should know about the hire?
Is there anyone outside of the organization who have requirements related to the hire?

## Slide 84
If you list out stakeholders, C
If you do not list stakeholders, D

## Slide 85: Planning
Scope
Schedule
Cost
Quality
Resources
Communication
Risk
Procurement
Stakeholders

## Slide 86: Scope – North Star
External Requirements – Laws? Community?
Deliverables – Choosing new hire, orientation, 90 days
Boundaries – Assumptions, Constraints, Exclusions
Work Breakdown – Major steps/deliverables
What Does Done Look Like?

## Slide 87: Schedule
Start with the end in mind – Need new staff by X date
Determine timeline for each major step/deliverables
  Advertise
  Choose candidates and interview
  Selection/background checks
  New hire start date

## Slide 88: Cost & Quality
Cost for Advertising (free or pay)
Interview Questions
Hire Paperwork

## Slide 89: Resources
Experts
Staff
Colleagues
Internal Documents
Notes: Real estate agent

## Slide 90: Communication
Staff meetings
Memos
Emails
Timing – how often

## Slide 91
If you communicate throughout project, E
If you communicate at the beginning and end of the project, F

## Slide 92: Risk and Procurement
What risk is there in hiring new staff?
What needs to be purchased before/after hire?
What are purchasing requirements?

## Slide 93: Stakeholders
Did you choose C or D?

## Slide 94: Stakeholders
Who is impacted by the hire?
Who must change workflows because of hire?
Is there anyone outside of the organization who should know about the hire?
Is there anyone outside of the organization who have requirements related to the hire?

## Slide 95: Execution
Direct and Manage Work
Manage Project Knowledge
Manage Quality
Acquire Resources
Develop and Manage Team
Manage Communications
Implement Risk Response
Conduct Procurements
Manage Stakeholder Engagement

## Slide 96: Direct and Manage Work
Track Progress of Deliverables
  Advertisement
  Candidate interviews
  Selection/background checks
  New hire start date
Track Changes in Plan
Tools: SharePoint, Monday, Excel, Meetings

## Slide 97: Project Charter
Did you choose A or B?
Notes: Do you really have the authority?

## Slide 98: Quality
Advertisement
Metrics

## Slide 99: Resources - Team
Virtual or In-person
Team Charter
Assignments
Schedules
Training
Team Building

## Slide 100: Communication
Did you choose E or F?
Notes: All the time or Now/Later? How does that play out?

## Slide 101: Communication
Tools: Email, Whiteboard, Newsletter, Meetings
Training
Reporting on Hiring Status

## Slide 102: Risk and Procurement
Risk Mitigation – coverage of duties
Risk Becomes Issue - when it happens
Purchasing – RFP, RFB, Quotes
Contracts

## Slide 103: Stakeholders
Engagement
Feedback
Updates

## Slide 104: Monitor and Control
Change Management
Validate and Control Scope
Schedule
Costs
Quality
Resources
Communication and Risk
Procurements
Stakeholders

## Slide 105: Quality
Data Analysis
Metrics
Audits
Testing Outcomes

## Slide 106: Change Management
Explain Change to Stakeholders
Plan for Resistance and Manage
Communicate, Ask for Feedback
Champion of Change

## Slide 107: Scope
Validate – Back to “What does done look like?”
Control (Scope creep)

## Slide 108: Schedule
On Task
On Time

## Slide 109: Costs
Advertisements
Equipment/Supplies

## Slide 110: Quality
Metrics for Done

## Slide 111: Resources
Bottlenecks?

## Slide 112: Communication
Communication According to Plan
Need More? Less?
Is the Earlier Decision Affecting Hiring of Staff?

## Slide 113: Risk and Procurement
Have Any Risks Become Issues?
Purchases Made As Needed?

## Slide 114: Stakeholders
Engaged?
Interest and Influence Managed?
Anyone We Missed?

## Slide 115: Close Out Hire Staff
Staff Hired
Lessons Learned
Home
End

## Slide 116: Project Management Tools
Microsoft Office:
  Excel
  To Do
  Planner
  Project
  OneNote
Dedicated Software – for multiple projects
  Monday
  ClickUp
  BaseCamp
  Trello
SmartSheets
Google Docs

## Slide 117: Project Management Recap
Initiate
  Authority
  Stakeholders
Plan
Execute
Monitor/Control
Scope
Schedule
Cost
Quality
Resources
Communication
Risk
Procurement
Stakeholders

## Slide 118: Thank you
Crystal Miner/ 907-232-9406
crystal@cbusinessak.com
www.cbusinessak.com